## Dashboard
Star Energy CEMS — MVP Cost Tracker
2-terminal parallel build • Claude Max 20x • $20/hr • 6-week MVP
Section | Metric | Estimated (USD) | Actual (USD) | Variance (USD) | % of Build
LABOR
Labor | Claude work-hours (MVP in-scope)
Labor | Your effective hours (÷ 1.4)
Labor | TOTAL LABOR COST @ $20/hr
CLAUDE & TOOLS
Claude | Claude Max 20x × 2 months
Claude | Production LLM API (MVP — zero) | 0
INFRASTRUCTURE
Infra | Azure dev (2 months minimum tiers)
Infra | Azure prod (launch month)
Infra | Third-party services (2 months)
ONE-TIME
Setup | Domain + legal templates + training
SUBTOTAL (before contingency)
Contingency (15%)
TOTAL TO LAUNCH MVP
CASH OUT-OF-POCKET | Cash only (excludes your sweat-equity labor)
YEAR 1 OPS | Year 1 production run-rate (post-launch)
GRAND TOTAL YEAR 1 (build + run)
SCENARIOS
Scenario | Description | Total (USD)
Lean | Scope held, no contingency burned
Realistic | This dashboard (default)
Slow | Part-time 25hr/wk → 10 weeks calendar
Scope creep | HVAC + Lighting + Envelope added back
NEXT ACTIONS
1. Finalize Epic 0 spikes (RLS, Puppeteer, Redis) before forking terminals
2. Confirm Terminal A/B file-system split (see 10-terminal-execution-plan.md)
3. Log actual hours on 'Actuals Log' tab daily
4. Review assumptions weekly; update values as reality diverges
5. If contingency burns past 50% by Week 4 → cut more scope, not overrun

## Labor
Labor — MVP Stories (2-Terminal Parallel Plan)
Epic | Story ID | Story Name | Terminal | Claude Work Hrs | Your Rate (USD) | Est Cost (USD) | Actual Hrs | Actual Cost (USD) | Variance Hrs | Variance Cost | Status | Notes
Epic 0 | 0-1 | Turborepo monorepo + shared package scaffold | Done | 0 | 20 |  | 0 |  |  |  | done | Already shipped
Epic 0 | 0-2 | Azure infrastructure provisioning | Done | 0 | 20 |  | 0 |  |  |  | done | Already shipped
Epic 0 | 0-3 | Database schema + RLS foundation | Seq (A) | 12 | 20 |  | 12 |  |  |  | done | Sequential blocker — A alone
Epic 0 | 0-4 | Node.js API foundation + BullMQ | A | 12 | 20 |  | 12 |  |  |  | done | Completed 2026-04-28
Epic 0 | 0-5 | Python calculation service scaffold | A | 8 | 20 |  | 8 |  |  |  | done | Built despite deferral — needed for CI/CD integration (2026-04-28)
Epic 0 | 0-6 | CI/CD pipeline | A | 6 | 20 |  | 10 |  |  |  | done | Completed 2026-05-01; complex OIDC + slot-swap wiring
Epic 0 | 0-7 | Design tokens + minimal component library | B | 4 | 20 | [5 empty] | backlog | Tailwind defaults + 3-4 components
Epic 0 | 0-8 | Accessibility + testing infrastructure | DEFERRED | 0 | 20 | [5 empty] | deferred | V2 polish
Epic 1 | 1-1 | Login API + JWT issuance | A | 8 | 20 | [5 empty] | backlog
Epic 1 | 1-1b | Login UI screen | B | 6 | 20 | [5 empty] | backlog
Epic 1 | 1-2 | Role-based access API guards | A | 4 | 20 | [5 empty] | backlog | Auditor + admin roles only
Epic 1 | 1-2b | Route guards — frontend | B | 4 | 20 | [5 empty] | backlog
Epic 1 | 1-3 | Admin user management — auditors | A+B | 8 | 20 | [5 empty] | backlog | Simple CRUD + list
Epic 1 | 1-4 | Admin client management | DEFERRED | 0 | 20 | [5 empty] | deferred | No client accounts in MVP
Epic 2 | 2-1 | Store reference API | A | 6 | 20 | [5 empty] | backlog
Epic 2 | 2-1b | Store selector screen | B | 6 | 20 | [5 empty] | backlog
Epic 2 | 2-2 | Auto-fill + draft creation API | A | 8 | 20 | [5 empty] | backlog
Epic 2 | 2-2b | Auto-fill UI | B | 4 | 20 | [5 empty] | backlog
Epic 2 | 2-3 | Auto-save API endpoints | A | 6 | 20 | [5 empty] | backlog
Epic 2 | 2-3b | Auto-save frontend hook | B | 4 | 20 | [5 empty] | backlog
Epic 2 | 2-4 | Section overview + nav shell | B | 8 | 20 | [5 empty] | backlog
Epic 3 | 3-1 | Audit breadcrumb + machine room screen | B | 8 | 20 | [5 empty] | backlog
Epic 3 | 3-2 | Rack entry + duplication | DEFERRED | 0 | 20 | [5 empty] | deferred | V2 — single rack in MVP
Epic 3 | 3-3a | Compressor + regression API | A | 10 | 20 | [5 empty] | backlog | Regression DB lookup
Epic 3 | 3-3b | Compressor screens UI | B | 12 | 20 | [5 empty] | backlog
Epic 3 | 3-4 | Condenser + display case UI + API | A+B | 14 | 20 | [5 empty] | backlog | Walk-in coolers deferred
Epic 3 | 3-5 | Controller systems | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 3 | 3-6 | Multi-auditor locking | DEFERRED | 0 | 20 | [5 empty] | deferred | Single-auditor MVP
Epic 4 | 4-1 | Camera + PhotoCaptureField | B | 12 | 20 | [5 empty] | backlog
Epic 4 | 4-2 | Auto-tag + Azure Blob upload API | A | 10 | 20 | [5 empty] | backlog
Epic 4 | 4-3 | Additional photos + comments | B | 6 | 20 | [5 empty] | backlog
Epic 4 | 4-4 | Upload queue retry | DEFERRED | 0 | 20 | [5 empty] | deferred | Fail-loud MVP
Epic 5 | 5-1 | General section screens (minimal) | B | 6 | 20 | [5 empty] | backlog
Epic 5 | 5-2 | HVAC section | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 5 | 5-3 | Lighting + envelope | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 5 | 5-4 | Review + submit screen | B | 8 | 20 | [5 empty] | backlog
Epic 5 | 5-5 | Submission confirmation + email | A+B | 6 | 20 | [5 empty] | backlog | SendGrid free tier
Epic 6 | 6-1 | Store reference seed script | A | 3 | 20 | [5 empty] | backlog | SQL seed — no UI
Epic 6 | 6-2 | Compressor regression seed script | A | 3 | 20 | [5 empty] | backlog | SQL seed — no UI
Epic 6 | 6-3 | Weather data retrieval | DEFERRED | 0 | 20 | [5 empty] | deferred | Not needed without baseline
Epic 7 | 7-1 | Audit queue API + list UI (simple) | A+B | 6 | 20 | [5 empty] | backlog | No filters; simple list
Epic 7 | 7-2 | SLA timer + detail sheet | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 7 | 7-3 | State machine transitions | DEFERRED | 0 | 20 | [5 empty] | deferred | Simple transitions in MVP
Epic 7 | 7-4 | Photo lock enforcement | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 8 | 8-1 | ECM refrigeration calc | A | 24 | 20 | [5 empty] | backlog | Core calc — Node for MVP
Epic 8 | 8-2 | Energy baseline regression | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 8 | 8-3 | LLM anomaly flagging | DEFERRED | 0 | 20 | [5 empty] | deferred | V2 — biggest deferred feature
Epic 8 | 8-4 | Admin flag override | DEFERRED | 0 | 20 | [5 empty] | deferred | Needs 8-3
Epic 8 | 8-5 | Calc inputs/outputs view | B | 6 | 20 | [5 empty] | backlog | Basic read-only
Epic 9 | 9-1 | Puppeteer PDF renderer | A | 12 | 20 | [5 empty] | backlog | Self-contained HTML bundle
Epic 9 | 9-2a | Admin approve + publish API | A | 4 | 20 | [5 empty] | backlog
Epic 9 | 9-2b | Admin approve UI | B | 4 | 20 | [5 empty] | backlog
Epic 9 | 9-3 | Report immutability / versioning | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 9 | 9-4 | Client email on publish | A | 4 | 20 | [5 empty] | backlog | SendGrid
Epic 9 | 9-5 | Report regeneration | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 10 | 10-1 | Client portal dashboard | DEFERRED | 0 | 20 | [5 empty] | deferred | Email PDF instead
Epic 10 | 10-2 | Client portal report view | DEFERRED | 0 | 20 | [5 empty] | deferred | Email PDF instead
Epic 10 | 10-3 | Client portal ECM summary | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
Epic 10 | 10-4 | Client portal notifications | DEFERRED | 0 | 20 | [5 empty] | deferred | V2
MVP In-Scope Claude Work Hours
Terminal A sequential hours
Terminal B sequential hours
Calendar time (slower terminal = critical path)
|  | Your effective hours (÷ 1.4 parallel efficiency) |  |  | 20
MVP LABOR COST @ your rate

## Subscriptions
Subscriptions & Dev Tools (2-month MVP build)
Category | Item | Plan | Monthly (USD) | Months | Est Total (USD) | Actual Total (USD) | Variance (USD) | Vendor | Required?
Claude | Claude Code Max 20x | Max 20x | 200 | 2 |  |  |  | Anthropic | Required
Source Control | GitHub Free | Free | 0 | 2 |  |  |  | GitHub | Required
Design | Figma Free | Free | 0 | 2 |  |  |  | Figma | Optional
Password Mgmt | 1Password (optional) | Individual | 3 | 2 |  |  |  | 1Password | Optional
Error Tracking | Sentry Developer | Free | 0 | 2 |  |  |  | Sentry | Recommended
Project Mgmt | Notion / Linear | Free | 0 | 2 |  |  |  | Notion | Optional
Diagrams | Excalidraw | Free | 0 | 2 |  |  |  | Excalidraw | Optional
TOTAL (required only — Claude Max)
TOTAL (all lines)

## Infrastructure
Azure Infrastructure + Third-Party (MVP build period)
Environment | Service | Tier / SKU | Monthly (USD) | Months | Est Total (USD) | Actual (USD) | Variance (USD)
Dev | Azure SQL Database | Basic (5 DTU) | 5 | 2
Dev | Azure App Service (API + PDF combined) | B1 Linux | 13 | 2
Dev | Azure Static Web Apps x2 | Free tier | 0 | 2
Dev | Azure Blob Storage | Hot <5GB | 2 | 2
Dev | Azure Cache for Redis | Basic C0 | 17 | 2
Dev | Application Insights | Free tier | 0 | 2
Dev | Azure Key Vault | Standard | 3 | 2
Dev SUBTOTAL
Prod | Azure SQL Database | S0 (10 DTU) | 15 | 1
Prod | Azure App Service (API + PDF) | B2 Linux | 55 | 1
Prod | Azure Static Web Apps x2 | Standard | 9 | 1
Prod | Azure Blob Storage | Hot + 10GB | 5 | 1
Prod | Azure Cache for Redis | Basic C0 | 17 | 1
Prod | Application Insights | Pay-as-you-go | 10 | 1
Prod | Azure Key Vault | Standard | 3 | 1
Prod | Bandwidth / Egress | Canada Central | 5 | 1
Prod SUBTOTAL
3rd-party | SendGrid | Free (100/day) | 0 | 2
3rd-party | Weather API | NOT NEEDED (deferred) | 0 | 2
3rd-party | Domain (amortized) | .com | 1 | 2
3rd-party | Managed SSL | Azure (free) | 0 | 2
3rd-party SUBTOTAL
GRAND TOTAL (Dev + Prod launch + 3rd-party)

## One-Time
One-Time Costs (MVP launch)
Category | Item | Est (USD) | Actual (USD) | Variance (USD) | Required? | Notes
Branding | Logo + brand kit | 0 |  |  | Skip | Use text logo / existing Star Energy branding
Branding | Illustrations / icons | 0 |  |  | Skip | Free Heroicons / Lucide
Legal | T&Cs + Privacy (Termly template) | 50 |  |  | Recommended | PIPEDA basics
Legal | Lawyer review | 0 |  |  | Skip | Defer to post-MVP
Compliance | Security audit / pentest | 0 |  |  | Skip | Defer to pre-client-rollout
Compliance | SOC2 readiness | 0 |  |  | Skip | V2+
Domain | Primary domain (.com) | 15 |  |  | Required | Annual
Domain | Domain privacy | 0 |  |  | Optional | Often free
SSL | Managed SSL | 0 |  |  | Required | Azure App Service managed cert (free)
Setup | Backup / DR config | 0 |  |  | Required | SQL 7-day PITR included
Training | Auditor onboarding (doc + Loom) | 50 |  |  | Recommended
Training | Client rollout walkthrough | 0 |  |  | Skip | Defer until first client
Launch | Marketing / landing page | 0 |  |  | Skip | Not needed for internal tool
Contingency | Unknown unknowns buffer | 50 |  |  | Recommended | ~15% of one-time
TOTAL

## Production Run-Rate
Year 1 Production Run-Rate (post-launch)
Category | Line Item | Monthly (USD) | Annual (USD) | Notes
Infrastructure | Azure SQL (S0 → S1 after beta) | 15 |  | Upgrade when >100 audits/mo
Infrastructure | Azure App Service B2 (API + PDF) | 55 |  | Split only under memory pressure
Infrastructure | Azure Static Web Apps x2 Standard | 18 |  | Custom domain support
Infrastructure | Azure Blob Storage | 10 |  | Hot → Cool lifecycle after 90d
Infrastructure | Azure Cache for Redis (C0) | 17 |  | Upgrade to C1 if queue backs up
Infrastructure | Application Insights | 10 |  | Low initial traffic
Infrastructure | Key Vault + Monitor + bandwidth | 15 |  | Aggregated
INFRA SUBTOTAL
3rd-party | SendGrid Essentials (post-beta) | 20 |  | When >100 emails/day
3rd-party | Domain + managed SSL | 1 |  | $15/yr amortized
3rd-party | Sentry Developer (free tier) | 0 |  | Until >5k errors/mo
Backup | Extended backup retention | 5 |  | Beyond default 7 days
OPS SUBTOTAL
Contingency (10%)
MVP MONTHLY RUN-RATE
— V2 FUTURE ADD-ONS (not in MVP run-rate) —
V2 | Python calc service (separate plan) | 75 |  | When baseline calc ships
V2 | Claude API — LLM anomaly flagging | 10 |  | ~$0.05/audit × 200 audits
V2 | OpenWeatherMap Standard | 40 |  | For CDD/HDD baseline data
V2 | Client portal Static Web App | 9 |  | When Epic 10 ships
V2 MONTHLY DELTA

## Token Estimates
Claude Token Estimates (dev + future production)
Phase | Activity | Model | Input tokens | Output tokens | Cache Read % | Input $/M | Output $/M | Est Cost (USD)
Dev (sunk) | PRD generation (completed) | Sonnet 4.6 | 500000 | 80000 | 40% | 3 | 15
Dev (sunk) | Architecture (completed) | Sonnet 4.6 | 600000 | 100000 | 50% | 3 | 15
Dev (sunk) | Epics + stories (completed) | Sonnet 4.6 | 800000 | 200000 | 50% | 3 | 15
Dev (sunk) | UX design (completed) | Sonnet 4.6 | 600000 | 150000 | 40% | 3 | 15
Dev (MVP) | Per-story impl session (35 stories) | Sonnet 4.6 | 21000000 | 5250000 | 70% | 3 | 15
Dev (MVP) | Per-story review (35 stories) | Sonnet 4.6 | 7000000 | 1750000 | 60% | 3 | 15
Dev (MVP) | 2nd-terminal coordination premium | Sonnet 4.6 | 1500000 | 300000 | 70% | 3 | 15
Dev (MVP) | Debugging + rework buffer | Sonnet 4.6 | 1500000 | 300000 | 50% | 3 | 15
Prod MVP | LLM anomaly — NOT IN MVP | Sonnet 4.6 | 0 | 0 | 0% | 3 | 15
V2 (future) | LLM anomaly per audit | Sonnet 4.6 | 17000 | 2000 | 60% | 3 | 15
V2 (future) | 200 audits/mo monthly | Sonnet 4.6 | 3400000 | 400000 | 60% | 3 | 15
V2 (future) | If switch to Haiku 4.5 (200/mo) | Haiku 4.5 | 3400000 | 400000 | 60% | 1 | 5
V2 (future) | If switch to Opus 4.7 (200/mo) | Opus 4.7 | 3400000 | 400000 | 60% | 15 | 75
DEV MVP API-equivalent cost (covered by $400 Max sub)

## Assumptions
Assumptions (tune these to model scenarios)
ID | Assumption | Current Value | Sensitivity | If Wrong | Source
A1 | Your hourly rate | $20/hour | High | Every $5 change = ~$1,150 on project | User-stated
A2 | MVP Claude work-hours (all stories) | ~320 hours | High | +50 hrs = +$715 your time | Per-story estimates
A3 | 2-terminal parallelism efficiency | 1.4x | High | 1.2x = +$660; 1.6x = -$410 | Attention/review analysis
A4 | Your effective hours (320 / 1.4) | ~230 hours | High | Drives labor cost directly | Derived
A5 | Project duration — MVP build | 6 weeks full-time | High | +1 week = +$240 carry cost | 40 hrs/wk × 5.75 weeks
A6 | Calendar duration (build + launch) | 2 months | Medium | Launch month accounts for prod Azure | Plan assumption
A7 | Claude plan | Max 20x ($200/mo) | High | Pro = rate-limit hell with 2 terminals | Max 20x required
A8 | MVP scope | Refrigeration + PDF email | High | HVAC/Lighting added back = +150 hrs | Aggressive cut
A9 | Hired developer | No | Low | Post-MVP contractor possible $60/hr × 50hr = +$3k | LLM-first solo build
A10 | Audits per month at launch | <50 (beta) | Medium | >100 forces tier upgrades | Internal use initially
A11 | Azure region | Canada Central | Low | +/- 10% egress cost | Locked
A12 | Reserved instances | No (pay-as-you-go) | Medium | 1yr reserved = -30% infra | Revisit 6 months post-launch
A13 | Security audit pre-MVP-beta | Skipped | High | Blocker for enterprise clients | Internal MVP only
A14 | Legal lawyer review | Skipped (templates) | Medium | Needed before billing clients | Defer to V2
A15 | LLM anomaly flagging in MVP | Deferred to V2 | Medium | Save 24 hrs + $10/mo prod API | User-accepted cut
A16 | Client portal in MVP | Deferred to V2 | Medium | Email PDF replaces it | User-accepted cut
A17 | Python calc service | Consolidated into Node | Low | Simpler deployment | MVP simplification
A18 | SendGrid | Free tier | Low | >100 emails/day = +$20/mo | MVP beta volume
A19 | Weather API | Not needed in MVP | Low | Needed when baseline calc lands | Deferred
A20 | Contingency buffer | 15% | Medium | Risky = 25% | Standard PM practice
A21 | Epic 0 spikes completion | Before feature work | High | RLS failure = rebuild security model | Non-negotiable gate
A22 | Design tokens minimal (Tailwind) | Yes | Low | Save 6-8 hrs vs full system | MVP simplification

## Actuals Log
Actuals Log — record real spend as project progresses
Date | Category | Subcategory | Vendor | Description | Amount (USD) | Payment Method | Invoice # | Linked To | Notes
2026-04-19 | Labor | Planning | Self | PRD draft and architecture review
2026-04-20 | Labor | Story execution | Self | Story 0-1 Turborepo scaffold
2026-04-22 | Labor | Story execution | Self | Story 0-2 Azure infrastructure provisioning
2026-04-24 | Labor | Story execution | Self | Story 0-3 DB schema + RLS (partial)
2026-04-25 | Labor | Story execution | Self | Story 0-3 DB schema + RLS — completed (12 hrs est)
2026-04-28 | Labor | Story execution | Self | Story 0-4 Node.js API foundation + BullMQ — completed (12 hrs est)
2026-04-28 | Labor | Story execution | Self | Story 0-5 Python calc service scaffold — completed despite deferral (8 hrs est)
2026-05-01 | Labor | Story execution | Self | Story 0-6 CI/CD pipeline + OIDC/slot-swap — completed (10 hrs actual vs 6 est)
2026-04-30 | Subscriptions | Claude Max 20x | Anthropic | April subscription cycle | 200
| Subscriptions | GitHub Free | GitHub | No charge | 0
| Infrastructure | Azure dev environment | Microsoft | First bill ~30 days after provisioning
| One-time | Domain | TBD registrar | starenergy-cems.com (or similar) | 15
| One-time | Legal templates | Termly | T&Cs + Privacy | 50
TOTAL ACTUAL SPEND (cash)